## JC9000
HAMMOND - Hammond Construction
[33 empty] | Page: | 1 |  | of | 1
[33 empty] | Date: | Nov 21, 2025
[33 empty] | Time: | 10:38 AM EST
[11 empty] | Period: |  |  | 2023-11-01 | [5 empty] | to |  |  | 2026-11-21
[6 empty] | Budget | [5 empty] | Actual Period | [6 empty] | Actual To Date | [7 empty] | Forecast to Complete |  |  |  |  | Forecast
| Job Cost Code | Name |  |  | WM | Qty |  | Hrs |  | Prod |  | Hrs |  |  | Prod | % |  | Est/ Act | Qty |  | Hrs |  |  | Prod | % | Est/ Act | Qty | Prod |  | Hrs |  | Hrs |  |  | Variance
| Job | 7552.01
| 7552.01 | Cuyahoga Falls - General
| 01 | General Requirements
| 01-2000 | Supervision |  |  | NA | 0 |  | 4480 | 0 |  |  | 4364.5 |  |  | 0 | 0 |  | 0 | 0 |  | 4730.5 |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 4730.5 |  |  | 250.5
| 01-4000 | Temporary Protection |  |  | NA | 0 |  | 1057 | 0 |  |  | 1155 |  |  | 0 | 0 |  | 0 | 0 |  | 1155 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 1155 |  |  | 98
| 01-5000 | Cleanup & Hauling |  |  | NA | 0 |  | 3953 | 0 |  |  | 5990 |  |  | 0 | 0 |  | 0 | 0 |  | 6317 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 6317 |  |  | 2364
| General Requirements Total: | [5 empty] | 9490 | [5 empty] | 11509.5 | [7 empty] | 12202.5 |  |  |  | 0 |  |  |  |  | 0 |  | 12202.5 |  |  | 2712.5
| 06 | Wood, Plastics, Composites
| 06-2000 | Finish Carpentry |  |  | NA | 0 |  | 590 | 0 |  |  | 2097 |  |  | 0 | 0 |  | 0 | 0 |  | 2097 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 2097 |  |  | 1507
| Wood, Plastics, Composites Total: | [5 empty] | 590 | [5 empty] | 2097 | [7 empty] | 2097 |  |  |  | 0 |  |  |  |  | 0 |  | 2097 |  |  | 1507
| 07 | Thermal & Moisture Protection
| 07-2000 | Thermal Insulation |  |  | NA | 0 |  | 827 | 0 |  |  | 1227 |  |  | 0 | 0 |  | 0 | 0 |  | 1227 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 1227 |  |  | 400
| 07-2100 | EIFS |  |  | NA | 0 |  | 15 | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | -15
| 07-8100 | Firestopping |  |  | NA | 0 |  | 393 | 0 |  |  | 2274.5 |  |  | 0 | 0 |  | 0 | 0 |  | 2274.5 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 2274.5 |  |  | 1881.5
| 07-9100 | Expansion Control |  |  | NA | 0 |  | 106 | 0 |  |  | 72 |  |  | 0 | 0 |  | 0 | 0 |  | 72 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 72 |  |  | -34
| Thermal & Moisture Protection Total: | [5 empty] | 1341 | [5 empty] | 3573.5 | [7 empty] | 3573.5 |  |  |  | 0 |  |  |  |  | 0 |  | 3573.5 |  |  | 2232.5
| 08 | Openings
| 08-1100 | Install Frames |  |  | NA | 0 |  | 217 | 0 |  |  | 675 |  |  | 0 | 0 |  | 0 | 0 |  | 675 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 675 |  |  | 458
| 08-2000 | Access Doors |  |  | NA | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0
| 08-6050 | Stock & Sort Hardware |  |  | NA | 0 |  | 112 | 0 |  |  | 155 |  |  | 0 | 0 |  | 0 | 0 |  | 155 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 155 |  |  | 43
| Openings Total: | [5 empty] | 329 | [5 empty] | 830 | [7 empty] | 830 |  |  |  | 0 |  |  |  |  | 0 |  | 830 |  |  | 501
| 08-1010 | Stock and Sort Metal Doors & Frames |  |  | NA | 0 |  | 114 | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | -114
| 10 | Specialties
| 10-1000 | Visual Display Surfaces |  |  | NA | 0 |  | 773 | 0 |  |  | 817 |  |  | 0 | 0 |  | 0 | 0 |  | 817 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 817 |  |  | 44
| 10-2300 | Wall & Door Protection |  |  | NA | 0 |  | 311 | 0 |  |  | 311 |  |  | 0 | 0 |  | 0 | 0 |  | 311 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 311 |  |  | 0
| 10-2400 | Toilet & Bath Accessories |  |  | NA | 0 |  | 482 | 0 |  |  | 346 |  |  | 0 | 0 |  | 0 | 0 |  | 346 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 346 |  |  | -136
| 10-3100 | Fire Extinguishers |  |  | NA | 0 |  | 49 | 0 |  |  | 121 |  |  | 0 | 0 |  | 0 | 0 |  | 121 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 121 |  |  | 72
| 10-5400 | Flagpoles |  |  | NA | 0 |  | 42 | 0 |  |  | 9 |  |  | 0 | 0 |  | 0 | 0 |  | 9 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 9 |  |  | -33
| Specialties Total: | [5 empty] | 1657 | [5 empty] | 1604 | [7 empty] | 1604 |  |  |  | 0 |  |  |  |  | 0 |  | 1604 |  |  | -53
| 10-4050 | Locker Benches |  |  | NA | 0 |  | 98 | 0 |  |  | 159 |  |  | 0 | 0 |  | 0 | 0 |  | 159 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 159 |  |  | 61
| 10-5500 | Knox Box |  |  | NA | 0 |  | 9 | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | -9
| 11 | Equipment
| 11-1300 | Residential Appliances |  |  | NA | 0 |  | 120 | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | -120
| Equipment Total: | [5 empty] | 120 | [5 empty] | 0 | [7 empty] | 0 |  |  |  | 0 |  |  |  |  | 0 |  | 0 |  |  | -120
| 12 | Furnishings
| 12-2100 | Unload Casework |  |  | NA | 0 |  | 444 | 0 |  |  | 500.5 |  |  | 0 | 0 |  | 0 | 0 |  | 500.5 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 500.5 |  |  | 56.5
| 12-6000 | Site Furnishings |  |  | NA | 0 |  | 341 | 0 |  |  | 59 |  |  | 0 | 0 |  | 0 | 0 |  | 59 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 59 |  |  | -282
| Furnishings Total: | [5 empty] | 785 | [5 empty] | 559.5 | [7 empty] | 559.5 |  |  |  | 0 |  |  |  |  | 0 |  | 559.5 |  |  | -225.5
| Job | 7552.01
| Cuyahoga Falls - General Total: | [5 empty] | 14533 | [5 empty] | 20332.5 | [7 empty] | 21025.5 |  |  |  | 0 |  |  |  |  | 0 |  | 21025.5 |  |  | 6492.5
| Job | 7552.02
| 7552.02 | Cuyahoga Falls - Bldg 1
| 05 | Metals
| 05-4000 | Exterior CFMF |  |  | NA | 0 |  | 2183 | 0 |  |  | 1205.5 |  |  | 0 | 0 |  | 0 | 0 |  | 1948 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 1948 |  |  | -235
| Metals Total: | [5 empty] | 2183 | [5 empty] | 1205.5 | [7 empty] | 1948 |  |  |  | 0 |  |  |  |  | 0 |  | 1948 |  |  | -235
| 06 | Wood, Plastics, Composites
| 06-1400 | Blocking - Opening |  |  | NA | 0 |  | 605 | 0 |  |  | 599 |  |  | 0 | 0 |  | 0 | 0 |  | 647 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 647 |  |  | 42
| 06-1500 | Blocking - Roof |  |  | NA | 0 |  | 473 | 0 |  |  | 460 |  |  | 0 | 0 |  | 0 | 0 |  | 558 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 558 |  |  | 85
| Wood, Plastics, Composites Total: | [5 empty] | 1078 | [5 empty] | 1059 | [7 empty] | 1205 |  |  |  | 0 |  |  |  |  | 0 |  | 1205 |  |  | 127
| 09 | Finishes
| 09-1400 | Exterior Sheathing |  |  | NA | 0 |  | 1310 | 0 |  |  | 1007 |  |  | 0 | 0 |  | 0 | 0 |  | 1421 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 1421 |  |  | 111
| Finishes Total: | [5 empty] | 1310 | [5 empty] | 1007 | [7 empty] | 1421 |  |  |  | 0 |  |  |  |  | 0 |  | 1421 |  |  | 111
| Job | 7552.02
| Cuyahoga Falls - Bldg 1 Total: | [5 empty] | 4571 | [5 empty] | 3271.5 | [7 empty] | 4574 |  |  |  | 0 |  |  |  |  | 0 |  | 4574 |  |  | 3
| Job | 7552.03
| 7552.03 | Cuyahoga Falls - Bldg 2
| 05 | Metals
| 05-4000 | Exterior CFMF |  |  | NA | 0 |  | 230 | 0 |  |  | 606 |  |  | 0 | 0 |  | 0 | 0 |  | 606 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 606 |  |  | 376
| Metals Total: | [5 empty] | 230 | [5 empty] | 606 | [7 empty] | 606 |  |  |  | 0 |  |  |  |  | 0 |  | 606 |  |  | 376
| 06 | Wood, Plastics, Composites
| 06-1400 | Blocking - Opening |  |  | LS | 0 |  | 320 | 0 |  |  | 208 |  |  | 0 | 0 |  | 0 | 0 |  | 208 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 208 |  |  | -112
| 06-1500 | Blocking - Roof |  |  | NA | 0 |  | 499 | 0 |  |  | 289 |  |  | 0 | 0 |  | 0 | 0 |  | 289 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 289 |  |  | -210
| Wood, Plastics, Composites Total: | [5 empty] | 819 | [5 empty] | 497 | [7 empty] | 497 |  |  |  | 0 |  |  |  |  | 0 |  | 497 |  |  | -322
| 09 | Finishes
| 09-1400 | Exterior Sheathing |  |  | NA | 0 |  | 164 | 0 |  |  | 414 |  |  | 0 | 0 |  | 0 | 0 |  | 414 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 414 |  |  | 250
| Finishes Total: | [5 empty] | 164 | [5 empty] | 414 | [7 empty] | 414 |  |  |  | 0 |  |  |  |  | 0 |  | 414 |  |  | 250
| Job | 7552.03
| Cuyahoga Falls - Bldg 2 Total: | [5 empty] | 1213 | [5 empty] | 1517 | [7 empty] | 1517 |  |  |  | 0 |  |  |  |  | 0 |  | 1517 |  |  | 304
| Job | 7552.04
| 7552.04 | Cuyahoga Falls - Bldg 3
| 05 | Metals
| 05-4000 | Exterior CFMF |  |  | NA | 0 |  | 45 | 0 |  |  | 378 |  |  | 0 | 0 |  | 0 | 0 |  | 378 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 378 |  |  | 333
| Metals Total: | [5 empty] | 45 | [5 empty] | 378 | [7 empty] | 378 |  |  |  | 0 |  |  |  |  | 0 |  | 378 |  |  | 333
| 06 | Wood, Plastics, Composites
| 06-1400 | Blocking - Opening |  |  | NA | 0 |  | 458 | 0 |  |  | 212 |  |  | 0 | 0 |  | 0 | 0 |  | 212 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 212 |  |  | -246
| 06-1500 | Blocking - Roof |  |  | NA | 0 |  | 1025 | 0 |  |  | 242 |  |  | 0 | 0 |  | 0 | 0 |  | 242 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 242 |  |  | -783
| Wood, Plastics, Composites Total: | [5 empty] | 1483 | [5 empty] | 454 | [7 empty] | 454 |  |  |  | 0 |  |  |  |  | 0 |  | 454 |  |  | -1029
| 09 | Finishes
| 09-1400 | Exterior Sheathing |  |  | NA | 0 |  | 91 | 0 |  |  | 316 |  |  | 0 | 0 |  | 0 | 0 |  | 316 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 316 |  |  | 225
| Finishes Total: | [5 empty] | 91 | [5 empty] | 316 | [7 empty] | 316 |  |  |  | 0 |  |  |  |  | 0 |  | 316 |  |  | 225
| Job | 7552.04
| Cuyahoga Falls - Bldg 3 Total: | [5 empty] | 1619 | [5 empty] | 1148 | [7 empty] | 1148 |  |  |  | 0 |  |  |  |  | 0 |  | 1148 |  |  | -471
| Job | 7552.06
| 7552.06 | Cuyahoga Falls - Bldg 1 Lower Level
| 01 | General Requirements
| 01-2800 | Layout |  |  | NA | 0 |  | 13 | 0 |  |  | 9 |  |  | 0 | 0 |  | 0 | 0 |  | 9 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 9 |  |  | -4
| General Requirements Total: | [5 empty] | 13 | [5 empty] | 9 | [7 empty] | 9 |  |  |  | 0 |  |  |  |  | 0 |  | 9 |  |  | -4
| 06 | Wood, Plastics, Composites
| 06-1200 | Blocking - In Wall |  |  | NA | 0 |  | 11 | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | -11
| Wood, Plastics, Composites Total: | [5 empty] | 11 | [5 empty] | 0 | [7 empty] | 0 |  |  |  | 0 |  |  |  |  | 0 |  | 0 |  |  | -11
| 08 | Openings
| 08-1100 | Install Frames |  |  | NA | 0 |  | 36 | 0 |  |  | 38 |  |  | 0 | 0 |  | 0 | 0 |  | 38 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 38 |  |  | 2
| 08-1200 | Install Doors |  |  | NA | 0 |  | 14 | 0 |  |  | 10 |  |  | 0 | 0 |  | 0 | 0 |  | 10 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 10 |  |  | -4
| 08-6000 | Install Door Hardware |  |  | NA | 0 |  | 64 | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | -64
| Openings Total: | [5 empty] | 114 | [5 empty] | 48 | [7 empty] | 48 |  |  |  | 0 |  |  |  |  | 0 |  | 48 |  |  | -66
| 09 | Finishes
| 09-1000 | Metal Framing |  |  | NA | 0 |  | 131 | 0 |  |  | 280 |  |  | 0 | 0 |  | 0 | 0 |  | 280 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 280 |  |  | 149
| 09-1500 | Hang Drywall |  |  | NA | 0 |  | 90 | 0 |  |  | 129 |  |  | 0 | 0 |  | 0 | 0 |  | 129 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 129 |  |  | 39
| 09-1550 | Hang Drywall - Soffit |  |  | NA | 0 |  | 7 | 0 |  |  | 3 |  |  | 0 | 0 |  | 0 | 0 |  | 3 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 |  |  | -4
| 09-1600 | Gypsum Board Top-out |  |  | NA | 0 |  | 103 | 0 |  |  | 149 |  |  | 0 | 0 |  | 0 | 0 |  | 149 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 149 |  |  | 46
| 09-1700 | Gypsum Board Taping |  |  | NA | 0 |  | 178 | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | -178
| 09-3100 | Acoustical Ceiling Grid |  |  | NA | 0 |  | 142 | 0 |  |  | 157 |  |  | 0 | 0 |  | 0 | 0 |  | 157 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 157 |  |  | 15
| 09-3200 | Acoustical Ceiling Tile |  |  | NA | 0 |  | 52 | 0 |  |  | 45 |  |  | 0 | 0 |  | 0 | 0 |  | 45 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 45 |  |  | -7
| 09-3300 | Acoustical Ceiling - Cuts |  |  | NA | 0 |  | 35 | 0 |  |  | 68 |  |  | 0 | 0 |  | 0 | 0 |  | 68 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 68 |  |  | 33
| Finishes Total: | [5 empty] | 738 | [5 empty] | 831 | [7 empty] | 831 |  |  |  | 0 |  |  |  |  | 0 |  | 831 |  |  | 93
| 12 | Furnishings
| 12-2200 | Install Cabinets |  |  | NA | 0 |  | 54 | 0 |  |  | 138 |  |  | 0 | 0 |  | 0 | 0 |  | 138 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 138 |  |  | 84
| 12-2300 | Install Countertops |  |  | NA | 0 |  | 12 | 0 |  |  | 51 |  |  | 0 | 0 |  | 0 | 0 |  | 51 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 51 |  |  | 39
| Furnishings Total: | [5 empty] | 66 | [5 empty] | 189 | [7 empty] | 189 |  |  |  | 0 |  |  |  |  | 0 |  | 189 |  |  | 123
| Job | 7552.06
| Cuyahoga Falls - Bldg 1 Lower Level Total: | [5 empty] | 942 | [5 empty] | 1077 | [7 empty] | 1077 |  |  |  | 0 |  |  |  |  | 0 |  | 1077 |  |  | 135
| Job | 7552.07
| 7552.07 | Cuyahoga Falls - Bldg 1 1st Floor
| 01 | General Requirements
| 01-2800 | Layout |  |  | NA | 0 |  | 105 | 0 |  |  | 84 |  |  | 0 | 0 |  | 0 | 0 |  | 109 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 109 |  |  | 4
| General Requirements Total: | [5 empty] | 105 | [5 empty] | 84 | [7 empty] | 109 |  |  |  | 0 |  |  |  |  | 0 |  | 109 |  |  | 4
| 06 | Wood, Plastics, Composites
| 06-1200 | Blocking - In Wall |  |  | NA | 0 |  | 206 | 0 |  |  | 99 |  |  | 0 | 0 |  | 0 | 0 |  | 115 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 115 |  |  | -91
| Wood, Plastics, Composites Total: | [5 empty] | 206 | [5 empty] | 99 | [7 empty] | 115 |  |  |  | 0 |  |  |  |  | 0 |  | 115 |  |  | -91
| 08 | Openings
| 08-1100 | Install Frames |  |  | NA | 0 |  | 262 | 0 |  |  | 175 |  |  | 0 | 0 |  | 0 | 0 |  | 191 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 191 |  |  | -71
| 08-1200 | Install Doors |  |  | NA | 0 |  | 117 | 0 |  |  | 64 |  |  | 0 | 0 |  | 0 | 0 |  | 64 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 64 |  |  | -53
| 08-6000 | Install Door Hardware |  |  | NA | 0 |  | 534 | 0 |  |  | 210 |  |  | 0 | 0 |  | 0 | 0 |  | 210 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 210 |  |  | -324
| Openings Total: | [5 empty] | 913 | [5 empty] | 449 | [7 empty] | 465 |  |  |  | 0 |  |  |  |  | 0 |  | 465 |  |  | -448
| 09 | Finishes
| 09-1000 | Metal Framing |  |  | NA | 0 |  | 781 | 0 |  |  | 863.5 |  |  | 0 | 0 |  | 0 | 0 |  | 871.5 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 871.5 |  |  | 90.5
| 09-1100 | Soffit Framing |  |  | NA | 0 |  | 414 | 0 |  |  | 374 |  |  | 0 | 0 |  | 0 | 0 |  | 374 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 374 |  |  | -40
| 09-1500 | Hang Drywall |  |  | NA | 0 |  | 958 | 0 |  |  | 873 |  |  | 0 | 0 |  | 0 | 0 |  | 887 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 887 |  |  | -71
| 09-1550 | Hang Drywall - Soffit |  |  | NA | 0 |  | 282 | 0 |  |  | 177.5 |  |  | 0 | 0 |  | 0 | 0 |  | 177.5 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 177.5 |  |  | -104.5
| 09-1600 | Gypsum Board Top-out |  |  | NA | 0 |  | 1083 | 0 |  |  | 1271 |  |  | 0 | 0 |  | 0 | 0 |  | 1276.5 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 1276.5 |  |  | 193.5
| 09-1700 | Gypsum Board Taping |  |  | NA | 0 |  | 6 | 0 |  |  | 31 |  |  | 0 | 0 |  | 0 | 0 |  | 31 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 31 |  |  | 25
| 09-3100 | Acoustical Ceiling Grid |  |  | NA | 0 |  | 1013 | 0 |  |  | 615 |  |  | 0 | 0 |  | 0 | 0 |  | 615 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 615 |  |  | -398
| 09-3200 | Acoustical Ceiling Tile |  |  | NA | 0 |  | 359 | 0 |  |  | 177 |  |  | 0 | 0 |  | 0 | 0 |  | 177 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 177 |  |  | -182
| 09-3300 | Acoustical Ceiling - Cuts |  |  | NA | 0 |  | 259 | 0 |  |  | 150 |  |  | 0 | 0 |  | 0 | 0 |  | 150 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 150 |  |  | -109
| Finishes Total: | [5 empty] | 5155 | [5 empty] | 4532 | [7 empty] | 4559.5 |  |  |  | 0 |  |  |  |  | 0 |  | 4559.5 |  |  | -595.5
| 12 | Furnishings
| 12-2200 | Install Cabinets |  |  | NA | 0 |  | 488 | 0 |  |  | 440 |  |  | 0 | 0 |  | 0 | 0 |  | 440 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 440 |  |  | -48
| 12-2300 | Install Countertops |  |  | NA | 0 |  | 540 | 0 |  |  | 395 |  |  | 0 | 0 |  | 0 | 0 |  | 395 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 395 |  |  | -145
| Furnishings Total: | [5 empty] | 1028 | [5 empty] | 835 | [7 empty] | 835 |  |  |  | 0 |  |  |  |  | 0 |  | 835 |  |  | -193
| Job | 7552.07
| Cuyahoga Falls - Bldg 1 1st Floor Total: | [5 empty] | 7407 | [5 empty] | 5999 | [7 empty] | 6083.5 |  |  |  | 0 |  |  |  |  | 0 |  | 6083.5 |  |  | -1323.5
| Job | 7552.08
| 7552.08 | Cuyahoga Falls - Bldg 1 2nd Floor
| 01 | General Requirements
| 01-2800 | Layout |  |  | NA | 0 |  | 141 | 0 |  |  | 101 |  |  | 0 | 0 |  | 0 | 0 |  | 157 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 157 |  |  | 16
| General Requirements Total: | [5 empty] | 141 | [5 empty] | 101 | [7 empty] | 157 |  |  |  | 0 |  |  |  |  | 0 |  | 157 |  |  | 16
| 06 | Wood, Plastics, Composites
| 06-1200 | Blocking - In Wall |  |  | NA | 0 |  | 162 | 0 |  |  | 84 |  |  | 0 | 0 |  | 0 | 0 |  | 84 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 84 |  |  | -78
| Wood, Plastics, Composites Total: | [5 empty] | 162 | [5 empty] | 84 | [7 empty] | 84 |  |  |  | 0 |  |  |  |  | 0 |  | 84 |  |  | -78
| 08 | Openings
| 08-1100 | Install Frames |  |  | NA | 0 |  | 182 | 0 |  |  | 204 |  |  | 0 | 0 |  | 0 | 0 |  | 204 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 204 |  |  | 22
| 08-1200 | Install Doors |  |  | NA | 0 |  | 86 | 0 |  |  | 57 |  |  | 0 | 0 |  | 0 | 0 |  | 57 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 57 |  |  | -29
| 08-6000 | Install Door Hardware |  |  | NA | 0 |  | 391 | 0 |  |  | 143 |  |  | 0 | 0 |  | 0 | 0 |  | 143 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 143 |  |  | -248
| Openings Total: | [5 empty] | 659 | [5 empty] | 404 | [7 empty] | 404 |  |  |  | 0 |  |  |  |  | 0 |  | 404 |  |  | -255
| 09 | Finishes
| 09-1000 | Metal Framing |  |  | NA | 0 |  | 775 | 0 |  |  | 938.5 |  |  | 0 | 0 |  | 0 | 0 |  | 994.5 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 994.5 |  |  | 219.5
| 09-1100 | Soffit Framing |  |  | NA | 0 |  | 391 | 0 |  |  | 331 |  |  | 0 | 0 |  | 0 | 0 |  | 331 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 331 |  |  | -60
| 09-1500 | Hang Drywall |  |  | NA | 0 |  | 852 | 0 |  |  | 650 |  |  | 0 | 0 |  | 0 | 0 |  | 672.5 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 672.5 |  |  | -179.5
| 09-1550 | Hang Drywall - Soffit |  |  | NA | 0 |  | 182 | 0 |  |  | 114 |  |  | 0 | 0 |  | 0 | 0 |  | 114 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 114 |  |  | -68
| 09-1600 | Gypsum Board Top-out |  |  | NA | 0 |  | 1042 | 0 |  |  | 875.5 |  |  | 0 | 0 |  | 0 | 0 |  | 877.5 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 877.5 |  |  | -164.5
| 09-1700 | Gypsum Board Taping |  |  | NA | 0 |  | 5 | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 5 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 5 |  |  | 0
| 09-3100 | Acoustical Ceiling Grid |  |  | NA | 0 |  | 806 | 0 |  |  | 452 |  |  | 0 | 0 |  | 0 | 0 |  | 452 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 452 |  |  | -354
| 09-3200 | Acoustical Ceiling Tile |  |  | NA | 0 |  | 289 | 0 |  |  | 147 |  |  | 0 | 0 |  | 0 | 0 |  | 147 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 147 |  |  | -142
| 09-3300 | Acoustical Ceiling - Cuts |  |  | NA | 0 |  | 196 | 0 |  |  | 182 |  |  | 0 | 0 |  | 0 | 0 |  | 182 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 182 |  |  | -14
| Finishes Total: | [5 empty] | 4538 | [5 empty] | 3690 | [7 empty] | 3775.5 |  |  |  | 0 |  |  |  |  | 0 |  | 3775.5 |  |  | -762.5
| 12 | Furnishings
| 12-2200 | Install Cabinets |  |  | NA | 0 |  | 780 | 0 |  |  | 540 |  |  | 0 | 0 |  | 0 | 0 |  | 540 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 540 |  |  | -240
| 12-2300 | Install Countertops |  |  | NA | 0 |  | 130 | 0 |  |  | 246 |  |  | 0 | 0 |  | 0 | 0 |  | 246 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 246 |  |  | 116
| Furnishings Total: | [5 empty] | 910 | [5 empty] | 786 | [7 empty] | 786 |  |  |  | 0 |  |  |  |  | 0 |  | 786 |  |  | -124
| Job | 7552.08
| Cuyahoga Falls - Bldg 1 2nd Floor Total: | [5 empty] | 6410 | [5 empty] | 5065 | [7 empty] | 5206.5 |  |  |  | 0 |  |  |  |  | 0 |  | 5206.5 |  |  | -1203.5
| Job | 7552.09
| 7552.09 | Cuyahoga Falls - Bldg 1 3rd Floor
| 01 | General Requirements
| 01-2800 | Layout |  |  | NA | 0 |  | 107 | 0 |  |  | 85 |  |  | 0 | 0 |  | 0 | 0 |  | 125 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 125 |  |  | 18
| General Requirements Total: | [5 empty] | 107 | [5 empty] | 85 | [7 empty] | 125 |  |  |  | 0 |  |  |  |  | 0 |  | 125 |  |  | 18
| 06 | Wood, Plastics, Composites
| 06-0010 | FRP Dome Install |  |  | LS | 0 |  | 191 | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 191 |  | 191 |  |  | 0
| 06-1200 | Blocking - In Wall |  |  | NA | 0 |  | 216 | 0 |  |  | 216 |  |  | 0 | 0 |  | 0 | 0 |  | 216 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 216 |  |  | 0
| Wood, Plastics, Composites Total: | [5 empty] | 407 | [5 empty] | 216 | [7 empty] | 216 |  |  |  | 0 |  |  |  |  | 191 |  | 407 |  |  | 0
| 08 | Openings
| 08-1100 | Install Frames |  |  | NA | 0 |  | 197 | 0 |  |  | 233 |  |  | 0 | 0 |  | 0 | 0 |  | 233 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 233 |  |  | 36
| 08-1200 | Install Doors |  |  | NA | 0 |  | 85 | 0 |  |  | 69 |  |  | 0 | 0 |  | 0 | 0 |  | 69 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 69 |  |  | -16
| 08-6000 | Install Door Hardware |  |  | NA | 0 |  | 387 | 0 |  |  | 205 |  |  | 0 | 0 |  | 0 | 0 |  | 205 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 205 |  |  | -182
| Openings Total: | [5 empty] | 669 | [5 empty] | 507 | [7 empty] | 507 |  |  |  | 0 |  |  |  |  | 0 |  | 507 |  |  | -162
| 09 | Finishes
| 09-1000 | Metal Framing |  |  | NA | 0 |  | 1372.5 | 0 |  |  | 1373.5 |  |  | 0 | 0 |  | 0 | 0 |  | 1563.5 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 1563.5 |  |  | 191
| 09-1100 | Soffit Framing |  |  | NA | 0 |  | 448.5 | 0 |  |  | 486.5 |  |  | 0 | 0 |  | 0 | 0 |  | 486.5 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 486.5 |  |  | 38
| 09-1500 | Hang Drywall |  |  | NA | 0 |  | 797 | 0 |  |  | 882 |  |  | 0 | 0 |  | 0 | 0 |  | 882 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 882 |  |  | 85
| 09-1550 | Hang Drywall - Soffit |  |  | NA | 0 |  | 167 | 0 |  |  | 175 |  |  | 0 | 0 |  | 0 | 0 |  | 175 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 175 |  |  | 8
| 09-1600 | Gypsum Board Top-out |  |  | NA | 0 |  | 1097 | 0 |  |  | 1569 |  |  | 0 | 0 |  | 0 | 0 |  | 1569 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 1569 |  |  | 472
| 09-1700 | Gypsum Board Taping |  |  | NA | 0 |  | 11 | 0 |  |  | 10 |  |  | 0 | 0 |  | 0 | 0 |  | 12.5 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 12.5 |  |  | 1.5
| 09-3100 | Acoustical Ceiling Grid |  |  | NA | 0 |  | 729 | 0 |  |  | 502 |  |  | 0 | 0 |  | 0 | 0 |  | 502 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 502 |  |  | -227
| 09-3200 | Acoustical Ceiling Tile |  |  | NA | 0 |  | 230 | 0 |  |  | 112 |  |  | 0 | 0 |  | 0 | 0 |  | 112 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 112 |  |  | -118
| 09-3300 | Acoustical Ceiling - Cuts |  |  | NA | 0 |  | 212 | 0 |  |  | 326.5 |  |  | 0 | 0 |  | 0 | 0 |  | 326.5 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 326.5 |  |  | 114.5
| Finishes Total: | [5 empty] | 5064 | [5 empty] | 5436.5 | [7 empty] | 5629 |  |  |  | 0 |  |  |  |  | 0 |  | 5629 |  |  | 565
| 12 | Furnishings
| 12-2200 | Install Cabinets |  |  | NA | 0 |  | 695 | 0 |  |  | 664.5 |  |  | 0 | 0 |  | 0 | 0 |  | 664.5 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 664.5 |  |  | -30.5
| 12-2300 | Install Countertops |  |  | NA | 0 |  | 81 | 0 |  |  | 292 |  |  | 0 | 0 |  | 0 | 0 |  | 292 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 292 |  |  | 211
| Furnishings Total: | [5 empty] | 776 | [5 empty] | 956.5 | [7 empty] | 956.5 |  |  |  | 0 |  |  |  |  | 0 |  | 956.5 |  |  | 180.5
| Job | 7552.09
| Cuyahoga Falls - Bldg 1 3rd Floor Total: | [5 empty] | 7023 | [5 empty] | 7201 | [7 empty] | 7433.5 |  |  |  | 0 |  |  |  |  | 191 |  | 7624.5 |  |  | 601.5
| Job | 7552.10
| 7552.10 | Cuyahoga Falls - Bldg 2 1st Floor
| 01 | General Requirements
| 01-2800 | Layout |  |  | NA | 0 |  | 5 | 0 |  |  | 36 |  |  | 0 | 0 |  | 0 | 0 |  | 36 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 36 |  |  | 31
| General Requirements Total: | [5 empty] | 5 | [5 empty] | 36 | [7 empty] | 36 |  |  |  | 0 |  |  |  |  | 0 |  | 36 |  |  | 31
| 06 | Wood, Plastics, Composites
| 06-1200 | Blocking - In Wall |  |  | NA | 0 |  | 73 | 0 |  |  | 23 |  |  | 0 | 0 |  | 0 | 0 |  | 23 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 23 |  |  | -50
| Wood, Plastics, Composites Total: | [5 empty] | 73 | [5 empty] | 23 | [7 empty] | 23 |  |  |  | 0 |  |  |  |  | 0 |  | 23 |  |  | -50
| 08 | Openings
| 08-1100 | Install Frames |  |  | NA | 0 |  | 85 | 0 |  |  | 145 |  |  | 0 | 0 |  | 0 | 0 |  | 190 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 190 |  |  | 105
| 08-1200 | Install Doors |  |  | NA | 0 |  | 31 | 0 |  |  | 34 |  |  | 0 | 0 |  | 0 | 0 |  | 34 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 34 |  |  | 3
| 08-6000 | Install Door Hardware |  |  | NA | 0 |  | 139 | 0 |  |  | 201 |  |  | 0 | 0 |  | 0 | 0 |  | 201 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 201 |  |  | 62
| Openings Total: | [5 empty] | 255 | [5 empty] | 380 | [7 empty] | 425 |  |  |  | 0 |  |  |  |  | 0 |  | 425 |  |  | 170
| 09 | Finishes
| 09-1000 | Metal Framing |  |  | NA | 0 |  | 20 | 0 |  |  | 260 |  |  | 0 | 0 |  | 0 | 0 |  | 260 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 260 |  |  | 240
| 09-1100 | Soffit Framing |  |  | NA | 0 |  | 88 | 0 |  |  | 163 |  |  | 0 | 0 |  | 0 | 0 |  | 163 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 163 |  |  | 75
| 09-1500 | Hang Drywall |  |  | NA | 0 |  | 13 | 0 |  |  | 291 |  |  | 0 | 0 |  | 0 | 0 |  | 291 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 291 |  |  | 278
| 09-1550 | Hang Drywall - Soffit |  |  | NA | 0 |  | 51 | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | -51
| 09-1600 | Gypsum Board Top-out |  |  | NA | 0 |  | 8 | 0 |  |  | 361 |  |  | 0 | 0 |  | 0 | 0 |  | 361 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 361 |  |  | 353
| 09-1700 | Gypsum Board Taping |  |  | NA | 0 |  | 57 | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | -57
| 09-3100 | Acoustical Ceiling Grid |  |  | NA | 0 |  | 135.5 | 0 |  |  | 332 |  |  | 0 | 0 |  | 0 | 0 |  | 332 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 332 |  |  | 196.5
| 09-3200 | Acoustical Ceiling Tile |  |  | NA | 0 |  | 46 | 0 |  |  | 92.5 |  |  | 0 | 0 |  | 0 | 0 |  | 92.5 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 92.5 |  |  | 46.5
| 09-3300 | Acoustical Ceiling - Cuts |  |  | NA | 0 |  | 37 | 0 |  |  | 86 |  |  | 0 | 0 |  | 0 | 0 |  | 86 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 86 |  |  | 49
| Finishes Total: | [5 empty] | 455.5 | [5 empty] | 1585.5 | [7 empty] | 1585.5 |  |  |  | 0 |  |  |  |  | 0 |  | 1585.5 |  |  | 1130
| 12 | Furnishings
| 12-2200 | Install Cabinets |  |  | NA | 0 |  | 3 | 0 |  |  | 141 |  |  | 0 | 0 |  | 0 | 0 |  | 141 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 141 |  |  | 138
| 12-2300 | Install Countertops |  |  | NA | 0 |  | 306 | 0 |  |  | 108 |  |  | 0 | 0 |  | 0 | 0 |  | 108 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 108 |  |  | -198
| Furnishings Total: | [5 empty] | 309 | [5 empty] | 249 | [7 empty] | 249 |  |  |  | 0 |  |  |  |  | 0 |  | 249 |  |  | -60
| Job | 7552.10
| Cuyahoga Falls - Bldg 2 1st Floor Total: | [5 empty] | 1097.5 | [5 empty] | 2273.5 | [7 empty] | 2318.5 |  |  |  | 0 |  |  |  |  | 0 |  | 2318.5 |  |  | 1221
| Job | 7552.11
| 7552.11 | Cuyahoga Falls - Bldg 2 2nd Floor
| 06 | Wood, Plastics, Composites
| 06-1200 | Blocking - In Wall |  |  | NA | 0 |  | 46 | 0 |  |  | 31 |  |  | 0 | 0 |  | 0 | 0 |  | 31 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 31 |  |  | -15
| Wood, Plastics, Composites Total: | [5 empty] | 46 | [5 empty] | 31 | [7 empty] | 31 |  |  |  | 0 |  |  |  |  | 0 |  | 31 |  |  | -15
| 08 | Openings
| 08-1100 | Install Frames |  |  | NA | 0 |  | 126 | 0 |  |  | 198 |  |  | 0 | 0 |  | 0 | 0 |  | 198 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 198 |  |  | 72
| 08-1200 | Install Doors |  |  | NA | 0 |  | 23 | 0 |  |  | 101 |  |  | 0 | 0 |  | 0 | 0 |  | 101 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 101 |  |  | 78
| 08-6000 | Install Door Hardware |  |  | NA | 0 |  | 91 | 0 |  |  | 134 |  |  | 0 | 0 |  | 0 | 0 |  | 134 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 134 |  |  | 43
| Openings Total: | [5 empty] | 240 | [5 empty] | 433 | [7 empty] | 433 |  |  |  | 0 |  |  |  |  | 0 |  | 433 |  |  | 193
| 09 | Finishes
| 09-1000 | Metal Framing |  |  | NA | 0 |  | 165 | 0 |  |  | 609 |  |  | 0 | 0 |  | 0 | 0 |  | 609 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 609 |  |  | 444
| 09-1100 | Soffit Framing |  |  | NA | 0 |  | 57 | 0 |  |  | 224 |  |  | 0 | 0 |  | 0 | 0 |  | 224 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 224 |  |  | 167
| 09-1500 | Hang Drywall |  |  | NA | 0 |  | 132 | 0 |  |  | 224 |  |  | 0 | 0 |  | 0 | 0 |  | 224 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 224 |  |  | 92
| 09-1550 | Hang Drywall - Soffit |  |  | NA | 0 |  | 91 | 0 |  |  | 57 |  |  | 0 | 0 |  | 0 | 0 |  | 57 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 57 |  |  | -34
| 09-1600 | Gypsum Board Top-out |  |  | NA | 0 |  | 152 | 0 |  |  | 791 |  |  | 0 | 0 |  | 0 | 0 |  | 791 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 791 |  |  | 639
| 09-1700 | Gypsum Board Taping |  |  | NA | 0 |  | 269 | 0 |  |  | 2 |  |  | 0 | 0 |  | 0 | 0 |  | 2 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 2 |  |  | -267
| 09-3100 | Acoustical Ceiling Grid |  |  | NA | 0 |  | 172 | 0 |  |  | 331 |  |  | 0 | 0 |  | 0 | 0 |  | 331 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 331 |  |  | 159
| 09-3200 | Acoustical Ceiling Tile |  |  | NA | 0 |  | 45 | 0 |  |  | 161 |  |  | 0 | 0 |  | 0 | 0 |  | 161 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 161 |  |  | 116
| 09-3300 | Acoustical Ceiling - Cuts |  |  | NA | 0 |  | 40 | 0 |  |  | 120 |  |  | 0 | 0 |  | 0 | 0 |  | 120 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 120 |  |  | 80
| Finishes Total: | [5 empty] | 1123 | [5 empty] | 2519 | [7 empty] | 2519 |  |  |  | 0 |  |  |  |  | 0 |  | 2519 |  |  | 1396
| 12 | Furnishings
| 12-2200 | Install Cabinets |  |  | NA | 0 |  | 54 | 0 |  |  | 199 |  |  | 0 | 0 |  | 0 | 0 |  | 199 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 199 |  |  | 145
| 12-2300 | Install Countertops |  |  | NA | 0 |  | 32 | 0 |  |  | 147 |  |  | 0 | 0 |  | 0 | 0 |  | 147 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 147 |  |  | 115
| Furnishings Total: | [5 empty] | 86 | [5 empty] | 346 | [7 empty] | 346 |  |  |  | 0 |  |  |  |  | 0 |  | 346 |  |  | 260
| Job | 7552.11
| Cuyahoga Falls - Bldg 2 2nd Floor Total: | [5 empty] | 1495 | [5 empty] | 3329 | [7 empty] | 3329 |  |  |  | 0 |  |  |  |  | 0 |  | 3329 |  |  | 1834
| Job | 7552.12
| 7552.12 | Cuyahoga Falls - Bldg 2 3rd Floor
| 09 | Finishes
| 09-1550 | Hang Drywall - Soffit |  |  | NA | 0 |  | 83 | 0 |  |  | 29 |  |  | 0 | 0 |  | 0 | 0 |  | 29 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 29 |  |  | -54
| 09-1700 | Gypsum Board Taping |  |  | NA | 0 |  | 36 | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | -36
| 09-3100 | Acoustical Ceiling Grid |  |  | NA | 0 |  | 25 | 0 |  |  | 68 |  |  | 0 | 0 |  | 0 | 0 |  | 68 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 68 |  |  | 43
| Finishes Total: | [5 empty] | 144 | [5 empty] | 97 | [7 empty] | 97 |  |  |  | 0 |  |  |  |  | 0 |  | 97 |  |  | -47
| Job | 7552.12
| Cuyahoga Falls - Bldg 2 3rd Floor Total: | [5 empty] | 144 | [5 empty] | 97 | [7 empty] | 97 |  |  |  | 0 |  |  |  |  | 0 |  | 97 |  |  | -47
| Job | 7552.13
| 7552.13 | Cuyahoga Falls - Bldg 3 Lower Level
| 01 | General Requirements
| 01-2800 | Layout |  |  | NA | 0 |  | 4 | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | -4
| General Requirements Total: | [5 empty] | 4 | [5 empty] | 0 | [7 empty] | 0 |  |  |  | 0 |  |  |  |  | 0 |  | 0 |  |  | -4
| 06 | Wood, Plastics, Composites
| 06-1200 | Blocking - In Wall |  |  | NA | 0 |  | 36 | 0 |  |  | 20 |  |  | 0 | 0 |  | 0 | 0 |  | 20 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 20 |  |  | -16
| Wood, Plastics, Composites Total: | [5 empty] | 36 | [5 empty] | 20 | [7 empty] | 20 |  |  |  | 0 |  |  |  |  | 0 |  | 20 |  |  | -16
| 08 | Openings
| 08-1100 | Install Frames |  |  | NA | 0 |  | 11 | 0 |  |  | 85 |  |  | 0 | 0 |  | 0 | 0 |  | 85 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 85 |  |  | 74
| 08-1200 | Install Doors |  |  | NA | 0 |  | 3 | 0 |  |  | 17 |  |  | 0 | 0 |  | 0 | 0 |  | 17 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 17 |  |  | 14
| 08-6000 | Install Door Hardware |  |  | NA | 0 |  | 12 | 0 |  |  | 200 |  |  | 0 | 0 |  | 0 | 0 |  | 200 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 200 |  |  | 188
| Openings Total: | [5 empty] | 26 | [5 empty] | 302 | [7 empty] | 302 |  |  |  | 0 |  |  |  |  | 0 |  | 302 |  |  | 276
| 09 | Finishes
| 09-1000 | Metal Framing |  |  | NA | 0 |  | 38 | 0 |  |  | 95 |  |  | 0 | 0 |  | 0 | 0 |  | 95 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 95 |  |  | 57
| 09-1100 | Soffit Framing |  |  | NA | 0 |  | 13 | 0 |  |  | 101 |  |  | 0 | 0 |  | 0 | 0 |  | 101 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 101 |  |  | 88
| 09-1500 | Hang Drywall |  |  | NA | 0 |  | 68.5 | 0 |  |  | 148 |  |  | 0 | 0 |  | 0 | 0 |  | 148 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 148 |  |  | 79.5
| 09-1550 | Hang Drywall - Soffit |  |  | NA | 0 |  | 10 | 0 |  |  | 104 |  |  | 0 | 0 |  | 0 | 0 |  | 104 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 104 |  |  | 94
| 09-1600 | Gypsum Board Top-out |  |  | NA | 0 |  | 19 | 0 |  |  | 158 |  |  | 0 | 0 |  | 0 | 0 |  | 158 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 158 |  |  | 139
| 09-3100 | Acoustical Ceiling Grid |  |  | NA | 0 |  | 147 | 0 |  |  | 353 |  |  | 0 | 0 |  | 0 | 0 |  | 353 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 353 |  |  | 206
| 09-3200 | Acoustical Ceiling Tile |  |  | NA | 0 |  | 37 | 0 |  |  | 78 |  |  | 0 | 0 |  | 0 | 0 |  | 78 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 78 |  |  | 41
| 09-3300 | Acoustical Ceiling - Cuts |  |  | NA | 0 |  | 38 | 0 |  |  | 72 |  |  | 0 | 0 |  | 0 | 0 |  | 72 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 72 |  |  | 34
| Finishes Total: | [5 empty] | 370.5 | [5 empty] | 1109 | [7 empty] | 1109 |  |  |  | 0 |  |  |  |  | 0 |  | 1109 |  |  | 738.5
| 12 | Furnishings
| 12-2200 | Install Cabinets |  |  | NA | 0 |  | 11 | 0 |  |  | 12 |  |  | 0 | 0 |  | 0 | 0 |  | 12 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 12 |  |  | 1
| 12-2300 | Install Countertops |  |  | NA | 0 |  | 15 | 0 |  |  | 91 |  |  | 0 | 0 |  | 0 | 0 |  | 91 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 91 |  |  | 76
| Furnishings Total: | [5 empty] | 26 | [5 empty] | 103 | [7 empty] | 103 |  |  |  | 0 |  |  |  |  | 0 |  | 103 |  |  | 77
| Job | 7552.13
| Cuyahoga Falls - Bldg 3 Lower Level Total: | [5 empty] | 462.5 | [5 empty] | 1534 | [7 empty] | 1534 |  |  |  | 0 |  |  |  |  | 0 |  | 1534 |  |  | 1071.5
| Job | 7552.14
| 7552.14 | Cuyahoga Falls - Bldg 3 1st Floor
| 01 | General Requirements
| 01-2800 | Layout |  |  | NA | 0 |  | 3 | 0 |  |  | 8 |  |  | 0 | 0 |  | 0 | 0 |  | 8 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 8 |  |  | 5
| General Requirements Total: | [5 empty] | 3 | [5 empty] | 8 | [7 empty] | 8 |  |  |  | 0 |  |  |  |  | 0 |  | 8 |  |  | 5
| 08 | Openings
| 08-1100 | Install Frames |  |  | NA | 0 |  | 131 | 0 |  |  | 10 |  |  | 0 | 0 |  | 0 | 0 |  | 10 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 10 |  |  | -121
| 08-1200 | Install Doors |  |  | NA | 0 |  | 42 | 0 |  |  | 4 |  |  | 0 | 0 |  | 0 | 0 |  | 4 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 |  |  | -38
| 08-6000 | Install Door Hardware |  |  | NA | 0 |  | 191 | 0 |  |  | 16 |  |  | 0 | 0 |  | 0 | 0 |  | 16 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 16 |  |  | -175
| Openings Total: | [5 empty] | 364 | [5 empty] | 30 | [7 empty] | 30 |  |  |  | 0 |  |  |  |  | 0 |  | 30 |  |  | -334
| 09 | Finishes
| 09-1500 | Hang Drywall |  |  | NA | 0 |  | 27 | 0 |  |  | 60 |  |  | 0 | 0 |  | 0 | 0 |  | 60 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 60 |  |  | 33
| 09-1550 | Hang Drywall - Soffit |  |  | NA | 0 |  | 6 | 0 |  |  | 8 |  |  | 0 | 0 |  | 0 | 0 |  | 8 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 8 |  |  | 2
| 09-1600 | Gypsum Board Top-out |  |  | NA | 0 |  | 17 | 0 |  |  | 147 |  |  | 0 | 0 |  | 0 | 0 |  | 147 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 147 |  |  | 130
| 09-1700 | Gypsum Board Taping |  |  | NA | 0 |  | 45 | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | -45
| Finishes Total: | [5 empty] | 95 | [5 empty] | 215 | [7 empty] | 215 |  |  |  | 0 |  |  |  |  | 0 |  | 215 |  |  | 120
| 12 | Furnishings
| 12-2300 | Install Countertops |  |  | NA | 0 |  | 7 | 0 |  |  | 5 |  |  | 0 | 0 |  | 0 | 0 |  | 5 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 5 |  |  | -2
| Furnishings Total: | [5 empty] | 7 | [5 empty] | 5 | [7 empty] | 5 |  |  |  | 0 |  |  |  |  | 0 |  | 5 |  |  | -2
| Job | 7552.14
| Cuyahoga Falls - Bldg 3 1st Floor Total: | [5 empty] | 469 | [5 empty] | 258 | [7 empty] | 258 |  |  |  | 0 |  |  |  |  | 0 |  | 258 |  |  | -211
| Job | 7552.15
| 7552.15 | Cuyahoga Falls - Bldg 3 2nd Floor
| 09 | Finishes
| 09-1000 | Metal Framing |  |  | NA | 0 |  | 30 | 0 |  |  | 214 |  |  | 0 | 0 |  | 0 | 0 |  | 214 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 214 |  |  | 184
| 09-1100 | Soffit Framing |  |  | NA | 0 |  | 18 | 0 |  |  | 78 |  |  | 0 | 0 |  | 0 | 0 |  | 78 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 78 |  |  | 60
| 09-1500 | Hang Drywall |  |  | NA | 0 |  | 2 | 0 |  |  | 124 |  |  | 0 | 0 |  | 0 | 0 |  | 124 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 124 |  |  | 122
| Finishes Total: | [5 empty] | 50 | [5 empty] | 416 | [7 empty] | 416 |  |  |  | 0 |  |  |  |  | 0 |  | 416 |  |  | 366
| Job | 7552.15
| Cuyahoga Falls - Bldg 3 2nd Floor Total: | [5 empty] | 50 | [5 empty] | 416 | [7 empty] | 416 |  |  |  | 0 |  |  |  |  | 0 |  | 416 |  |  | 366
| Job | 7552.16
| 7552.16 | Cuyahoga Falls - Bldg 4 1st Floor
| 01 | General Requirements
| 01-2800 | Layout |  |  | NA | 0 |  | 58 | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | -58
| General Requirements Total: | [5 empty] | 58 | [5 empty] | 0 | [7 empty] | 0 |  |  |  | 0 |  |  |  |  | 0 |  | 0 |  |  | -58
| 06 | Wood, Plastics, Composites
| 06-1200 | Blocking - In Wall |  |  | NA | 0 |  | 1 | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | -1
| Wood, Plastics, Composites Total: | [5 empty] | 1 | [5 empty] | 0 | [7 empty] | 0 |  |  |  | 0 |  |  |  |  | 0 |  | 0 |  |  | -1
| 08 | Openings
| 08-1100 | Install Frames |  |  | NA | 0 |  | 201 | 0 |  |  | 129 |  |  | 0 | 0 |  | 0 | 0 |  | 129 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 129 |  |  | -72
| 08-1200 | Install Doors |  |  | NA | 0 |  | 52 | 0 |  |  | 80 |  |  | 0 | 0 |  | 0 | 0 |  | 80 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 80 |  |  | 28
| 08-6000 | Install Door Hardware |  |  | NA | 0 |  | 234 | 0 |  |  | 106 |  |  | 0 | 0 |  | 0 | 0 |  | 106 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 106 |  |  | -128
| Openings Total: | [5 empty] | 487 | [5 empty] | 315 | [7 empty] | 315 |  |  |  | 0 |  |  |  |  | 0 |  | 315 |  |  | -172
| 09 | Finishes
| 09-1000 | Metal Framing |  |  | NA | 0 |  | 165 | 0 |  |  | 81 |  |  | 0 | 0 |  | 0 | 0 |  | 81 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 81 |  |  | -84
| 09-1100 | Soffit Framing |  |  | NA | 0 |  | 18 | 0 |  |  | 38 |  |  | 0 | 0 |  | 0 | 0 |  | 38 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 38 |  |  | 20
| 09-1500 | Hang Drywall |  |  | NA | 0 |  | 2 | 0 |  |  | 320 |  |  | 0 | 0 |  | 0 | 0 |  | 320 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 320 |  |  | 318
| 09-1550 | Hang Drywall - Soffit |  |  | NA | 0 |  | 112 | 0 |  |  | 25 |  |  | 0 | 0 |  | 0 | 0 |  | 25 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 25 |  |  | -87
| 09-1600 | Gypsum Board Top-out |  |  | NA | 0 |  | 5 | 0 |  |  | 52 |  |  | 0 | 0 |  | 0 | 0 |  | 52 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 52 |  |  | 47
| 09-1700 | Gypsum Board Taping |  |  | NA | 0 |  | 32 | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | -32
| Finishes Total: | [5 empty] | 334 | [5 empty] | 516 | [7 empty] | 516 |  |  |  | 0 |  |  |  |  | 0 |  | 516 |  |  | 182
| 12 | Furnishings
| 12-2200 | Install Cabinets |  |  | NA | 0 |  | 424 | 0 |  |  | 357 |  |  | 0 | 0 |  | 0 | 0 |  | 357 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 357 |  |  | -67
| 12-2300 | Install Countertops |  |  | NA | 0 |  | 35 | 0 |  |  | 49 |  |  | 0 | 0 |  | 0 | 0 |  | 49 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 49 |  |  | 14
| Furnishings Total: | [5 empty] | 459 | [5 empty] | 406 | [7 empty] | 406 |  |  |  | 0 |  |  |  |  | 0 |  | 406 |  |  | -53
| Job | 7552.16
| Cuyahoga Falls - Bldg 4 1st Floor Total: | [5 empty] | 1339 | [5 empty] | 1237 | [7 empty] | 1237 |  |  |  | 0 |  |  |  |  | 0 |  | 1237 |  |  | -102
| Job | 7552.17
| 7552.17 | Cuyahoga Falls - Alt 1 Bldg 4 Auditorium
| 05 | Metals
| 05-4000 | Exterior CFMF |  |  | NA | 0 |  | 199 | 0 |  |  | 236 |  |  | 0 | 0 |  | 0 | 0 |  | 1191 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 1191 |  |  | 992
| Metals Total: | [5 empty] | 199 | [5 empty] | 236 | [7 empty] | 1191 |  |  |  | 0 |  |  |  |  | 0 |  | 1191 |  |  | 992
| 06 | Wood, Plastics, Composites
| 06-1000 | Rough Carpentry |  |  | NA | 0 |  | 4 | 0 |  |  | 612 |  |  | 0 | 0 |  | 0 | 0 |  | 612 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 612 |  |  | 608
| 06-1200 | Blocking - In Wall |  |  | NA | 0 |  | 353 | 0 |  |  | 27 |  |  | 0 | 0 |  | 0 | 0 |  | 27 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 27 |  |  | -326
| 06-1500 | Blocking - Roof |  |  | NA | 0 |  | 325 | 0 |  |  | 359 |  |  | 0 | 0 |  | 0 | 0 |  | 383 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 383 |  |  | 58
| 06-2000 | Finish Carpentry |  |  | NA | 0 |  | 44 | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | -44
| Wood, Plastics, Composites Total: | [5 empty] | 726 | [5 empty] | 998 | [7 empty] | 1022 |  |  |  | 0 |  |  |  |  | 0 |  | 1022 |  |  | 296
| 07 | Thermal & Moisture Protection
| 07-2000 | Thermal Insulation |  |  | NA | 0 |  | 16 | 0 |  |  | 40 |  |  | 0 | 0 |  | 0 | 0 |  | 40 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 40 |  |  | 24
| Thermal & Moisture Protection Total: | [5 empty] | 16 | [5 empty] | 40 | [7 empty] | 40 |  |  |  | 0 |  |  |  |  | 0 |  | 40 |  |  | 24
| 08 | Openings
| 08-1100 | Install Frames |  |  | NA | 0 |  | 58 | 0 |  |  | 62 |  |  | 0 | 0 |  | 0 | 0 |  | 118 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 118 |  |  | 60
| 08-1200 | Install Doors |  |  | NA | 0 |  | 22 | 0 |  |  | 2 |  |  | 0 | 0 |  | 0 | 0 |  | 2 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 2 |  |  | -20
| 08-6000 | Install Door Hardware |  |  | NA | 0 |  | 69 | 0 |  |  | 2 |  |  | 0 | 0 |  | 0 | 0 |  | 2 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 2 |  |  | -67
| Openings Total: | [5 empty] | 149 | [5 empty] | 66 | [7 empty] | 122 |  |  |  | 0 |  |  |  |  | 0 |  | 122 |  |  | -27
| 09 | Finishes
| 09-1000 | Metal Framing |  |  | NA | 0 |  | 152 | 0 |  |  | 438 |  |  | 0 | 0 |  | 0 | 0 |  | 438 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 438 |  |  | 286
| 09-1400 | Exterior Sheathing |  |  | NA | 0 |  | 96 | 0 |  |  | 322 |  |  | 0 | 0 |  | 0 | 0 |  | 322 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 322 |  |  | 226
| 09-1500 | Hang Drywall |  |  | NA | 0 |  | 230 | 0 |  |  | 569 |  |  | 0 | 0 |  | 0 | 0 |  | 569 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 569 |  |  | 339
| 09-1550 | Hang Drywall - Soffit |  |  | NA | 0 |  | 215 | 0 |  |  | 16 |  |  | 0 | 0 |  | 0 | 0 |  | 16 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 16 |  |  | -199
| 09-1600 | Gypsum Board Top-out |  |  | NA | 0 |  | 34 | 0 |  |  | 81 |  |  | 0 | 0 |  | 0 | 0 |  | 81 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 81 |  |  | 47
| 09-1700 | Gypsum Board Taping |  |  | NA | 0 |  | 339 | 0 |  |  | 4 |  |  | 0 | 0 |  | 0 | 0 |  | 4 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 |  |  | -335
| 09-3100 | Acoustical Ceiling Grid |  |  | NA | 0 |  | 126 | 0 |  |  | 502 |  |  | 0 | 0 |  | 0 | 0 |  | 502 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 502 |  |  | 376
| 09-3200 | Acoustical Ceiling Tile |  |  | NA | 0 |  | 6 | 0 |  |  | 117 |  |  | 0 | 0 |  | 0 | 0 |  | 117 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 117 |  |  | 111
| 09-3300 | Acoustical Ceiling - Cuts |  |  | NA | 0 |  | 5 | 0 |  |  | 66 |  |  | 0 | 0 |  | 0 | 0 |  | 66 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 66 |  |  | 61
| Finishes Total: | [5 empty] | 1203 | [5 empty] | 2115 | [7 empty] | 2115 |  |  |  | 0 |  |  |  |  | 0 |  | 2115 |  |  | 912
| 10 | Specialties
| 10-2400 | Toilet & Bath Accessories |  |  | NA | 0 |  | 7 | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | -7
| Specialties Total: | [5 empty] | 7 | [5 empty] | 0 | [7 empty] | 0 |  |  |  | 0 |  |  |  |  | 0 |  | 0 |  |  | -7
| 12 | Furnishings
| 12-2300 | Install Countertops |  |  | NA | 0 |  | 27 | 0 |  |  | 21 |  |  | 0 | 0 |  | 0 | 0 |  | 21 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 21 |  |  | -6
| Furnishings Total: | [5 empty] | 27 | [5 empty] | 21 | [7 empty] | 21 |  |  |  | 0 |  |  |  |  | 0 |  | 21 |  |  | -6
| Job | 7552.17
| Cuyahoga Falls - Alt 1 Bldg 4 Auditorium Total: | [5 empty] | 2327 | [5 empty] | 3476 | [7 empty] | 4511 |  |  |  | 0 |  |  |  |  | 0 |  | 4511 |  |  | 2184
Report Parameters
| Pick List: | [15 empty] | Stating Cost Code: | [11 empty] | Run Date: |  | Nov 21, 2025
| Starting Job: |  | 7552.01 | [13 empty] | Ending Cost Code: | [11 empty] | Run Time: |  | 10:38 AM EST
| Ending Job: |  | 7552.17 | [13 empty] | Controlling Catagory: |  |  |  |  | L | [6 empty] | Operator: |  | HAMMOND¦¦MHUNT
| Session ID: |  | 5760583080 | [13 empty] | Report based on date: |  |  |  |  | REF | [6 empty] | Report Code: |  | JC9000 | [6 empty] | 203-2